TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR nnovation Data and Product Consultant with possible travel

Currency of the proposal: USD

| S. No. | Deliverables | Deadline for completion of deliverable | Details of Travel Required | Professional Fee (Daily) | Input Days | Total Professional Fee |  | Total Travel Cost |  | Total Amount (All Inclusive Fee) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (A) | (B) | (C) | (D) | (E) | (F = DxE) |  | (G) |  | (H = F+G) |  |
| 1. | Deliver the next version of the OOI Country Engagement application, based on user needs/research including enhancing data entry, processing, syncing with existing OOI databases, database architecture, and user interface. Tested with at least 5 users, all critical errors fixed, and in live use with user guidance. | 31 March 2027 |  | 300 | 25 | 7500 |  | 1250 |  | 8750 |  |
| 2 | Analyse agreed Country Office annual reports and other qualitative sources using a documented and validated AI-assisted method to assess UNICEF’s innovation footprint and maturity. Deliver the findings as visual or information products tailored to OOI audiences, with key findings validated by delivering at least one OOI sense-making session. | 31 March 2027 |  | 300 | 20 | 6000 |  | 0 |  | 6000 |  |
| 3 | Design and deliver an AI-assisted application or automation to support Monitoring, Evaluation and Learning (MEL) for innovation, for example by helping users identify and access relevant MEL tools and resources based on their needs. Tested with at least 5 users, all critical errors fixed, and deployed for use with user guidance. | 31 March 2027 |  | 300 | 20 | 6000 |  | 0 |  | 6000 |  |
| 4 | Map OOI’s existing Country Office data sources relevant to innovation and identify how they could help OOI better target and tailor its services and solutions. Deliver an overview of the most useful data sources and use cases, along with a solution concept or MVP (e.g., a data model, application prototype, or combined analysis). | 31 March 2027 |  | 300 | 15 | 4500 |  | 0 |  | 4500 |  |
| 5 | In collaboration with and under the guidance of the COMPASS programme team, refine and deliver the next iteration of the Innovation Capability Assessment (ICA) and Innovation Readiness Assessment (IRA) data services and dashboards, based on identified needs and demand, to improve how Country Offices and OOI can access, interpret and use the results. | 31 March 2027 |  | 300 | 20 | 6000 |  | 1250 |  | 7250 |  |
| 6 | Deliver an integrated portfolio data solution that connects relevant OOI data and tools around user needs and workflows, enabling users to link and explore innovation problems, solutions and insights through appropriate interfaces or dashboards. Complete the required data migration and ensure data is accurate, reliable and synced across sources. | 8 November 2027 |  | 300 | 30 | 9000 |  | 1250 |  | 10250 |  |
| 7 | Deliver the next version of the 5D Web Assessment Tool with AI features that can automate the collection, processing and visualisation of innovation data for both UNICEF and external users. Tested with at least 5 users, all critical errors fixed, and in live use with user guidance. | 8 November 2027 |  | 300 | 25 | 7500 |  | 0 |  | 7500 |  |
| 8 | Design and deliver an AI-assisted application that integrates the Innovation Knowledge Playbook and OOI’s portfolio knowledge base to help users find and generate insights from existing knowledge. Develop and test the application with at least 5 users, validate the quality and reliability of outputs, and deliver a working version with user guidance and a demo session. | 8 November 2027 |  | 300 | 25 | 7500 |  | 0 |  | 7500 |  |
| 9 | Deliver an improved iteration of the Country Engagement application, including enhanced user interface and search, and resolution of issues and functionality needed based on usage feedback. | 8 November 2027 |  | 300 | 15 | 4500 |  | 0 |  | 4500 |  |
| 10 | The Insights & Evidence team responds to emerging data and knowledge needs across OOI and Country Offices, which may require tailored solutions. Support and deliver at least 4 agreed solutions requiring data, analytics or product development, such as data products, analyses, dashboards, knowledge products, applications or automations. | 8 November 2027 |  | 300 | 25 | 7500 |  | 0 |  | 7500 |  |
|  | TOTAL AMOUNT |  |  |  |  |  | 66000 |  | 3750 |  | 69750 |  |

Note: Shaded cells shall be filled by the Applicants.

Notes to financial offer:

- Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.

- Air travel should be economy class using the most direct route.

- No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.

- The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones.

- All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Zhongli Wang

Signature of the Applicant: Click here

Address:  Astastrasse 22, 33617 Bielefeld, Germany

Contact no.:  +4916095416015

Email address:  nkwangzhongli@gmail.com

Date: 14.10.2026.